## Slide 1
Update on the 2018 Performance Framework Milestones

## Slide 2: Performance Framework & Reserve
In order to monitor progress towards the objectives and targets set for each priority axis under the 2014-2020 Programme, a number of financial and output indicators were included under a Performance Framework in order to establish clear, realistic and measurable milestones and targets set for 2018 and 2023.
Where there is evidence based on financial and output indicators of a serious failure in achieving a priority’s milestones due to implementation weaknesses, the Commission may suspend all or part of interim payments for that particular Priority Axis.
The MA’s monitoring of the projects’ progress in achieving the Performance Framework milestones for 2018, both financial and output, has been constant.

## Slide 3: Performance Framework - PA 1 Progress on Output Indicators
Output Indicator | Output Milestone for 2018 | Progress achieved to date
KIS: Number of research facilities being implemented (constructed) or completed | 2 | 2
The Output milestone for 2018 has been achieved through 2 projects approved to be implemented by the UoM:
Transdisciplinary Research and Knowledge Exchange Complex
Sustainable Living Complex
Notes: Performance Framework Indicator: Number of Research Facilities – Target 2023 – 3
This has been achieved through:
TRAKE – 1
SLC - 1

## Slide 4: Performance Framework - PA 1 Progress on Financial Indicators
Financial Milestone for 2018 | Progress achieved to date | Payments still needed till end 2018
€17.9M | €3.8M | €14.1M
The remaining forecasted disbursement of €14.1M is expected to be achieved by means of the 2 UoM projects approved under this PA as follows:
Circa €6.4M are to be processed from contracts that have been awarded;
Circa €9.9M are expected to be disbursed from tenders which are currently being evaluated.
Notes: Check all key implementation steps.

## Slide 5: Performance Framework - PA 2 Progress on Output Indicators
Output Indicator | Output Milestone for 2018 | Progress achieved to date
New e-services applications in the areas of health, environment, customs and interdepartmental services | 2 | 4
The Output milestone for 2018 has been achieved:
Institute for Education Online Portal (Converge)
New E-Courts Service (Converge)
Orthoimagery Tool (Sintegram)
Reprojection Tool (Sintegram)
Notes: Converge breakdown:​
​
2 achieved to date: ​
​
1. Institute for Education Online Portal – Will be launched on 19/11/2018​
2. Ecourts Service:​
eCourts Service - Hall Usage - https://ecourts.gov.mt/onlineservices/HallUsage​
eCourts Service - Auctions - https://ecourts.gov.mt/onlineservices/JudicialSales​
eCourts Service - Court Fees - https://ecourts.gov.mt/onlineservices/Claims​
eCourts Service - Judgements - https://ecourts.gov.mt/onlineservices/judgements ​
eCourts Service - Online Application – Commercial Courts - https://ecourts.gov.mt/onlineservices/JForms/StartForm/1 (you need to be registered as a legal procurator for this service)​
eCourts Service - Civil Forms - https://ecourts.gov.mt/onlineservices/CivilForms (you need to be registered as a legal professional for this service)​
​
2 to be achieved by end of year:​
​
Digital Tourism Platform – Tourist Information Office eService – will be ready by end of year​
eDisaster Management System – Will be ready by end of year ​
​
Sintegram breakdown: (still to be clarified – our interpretation is that there are 2)

## Slide 6: Performance Framework - PA 2 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date
€9.7M | €15.4M
The Financial milestone for 2018 has been achieved.

## Slide 7: Performance Framework - PA 3 Progress on Output Indicator
Output Indicator | Output Milestone for 2018 | Progress achieved to date
Productive Investment: Number of enterprises receiving support | 70 | 38
To date 38 enterprises received support through the Grant Schemes for the Private Sector.
Notes: 175 enterprises receiving [non financial] support through the Information Knowledge Platform set up by TradeMalta.

## Slide 8: Performance Framework – PA 3 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date
€13.3M | €13.5M
The Financial milestone for 2018 has been achieved.
Notes: OP Change – Financial Target: €11,152,228.15

## Slide 9: Performance Framework – PA 4 Progress on Output Indicator
Output Indicator | Output Milestone for 2018 | Progress achieved to date
Additional capacity of renewable energy production (MW) | 7 | 15.34
Output Milestone achieved:
15.29MW from the RES domestic scheme
0.05MW from a project implemented by MITA.
Notes: OP Change – 10.64.
The indicator is being achieved through the following:
ERDF.04.008 (REWS) – 15.29;
ERDF.04.067 (MITA) – 0.05.

## Slide 10: Performance Framework – PA 4 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed till end 2018
€14.4M | €10.3M | €4.1M
The remaining forecasted disbursement amounting to €4.1M is expected to be disbursed as follows:
Domestic Household PV Scheme - €0.4M currently being processed whilst an additional €0.7M are expected to be processed;
Retrofitting of Streetlighting project - c. €1M expected to be processed;
Ministry for Gozo Administration centre - c. €0.4M expected to be processed following the recent award of the main works tender for the installation of energy efficient measures;
Moreover, discussions are ongoing for the finalisation of a Funding Agreement with EIF and EIB for the introduction of a Financial Instrument with a €15M allocation for energy efficiency actions.

## Slide 11: Performance Framework – PA 5 Progress on Output Indicator
Output Indicator | Output Milestone for 2018 | Progress achieved to date | Progress expected to be achieved by end 2018
Sustainable Tourism: Increase in expected number of visits to supported sites of cultural and natural heritage and attractions | 3,000 | 5,000* | -
Rehabilitated/Preserved Land** | 1,000 | - | -
The Output milestone for 2018 related to expected number of visits in supported sites is expected to be achieved through the contribution of the Manoel Theatre and MUZA projects.
* The 5,000 is expected to increase once a full calendar year is taken into account.
** The Output Milestone Indicator related to 'Rehabilitated/Preserved Land' is subject to a proposed OP modification.

## Slide 12: Performance Framework - PA 5 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed till end 2018
€17.9M | €11.8M | €6.1M
The remaining forecasted disbursement amounting to €6.1M are expected under the following projects:
MUZA: €3.3M as final payments;
Enhancing the Cultural Tourism Experience through Digitization: €0.5M through contracts being implemented;
Re-Living the Sacra Infermeria: €0.5M from tenders that are currently under evaluation or recently awarded;
Malta Carnival Experience: €0.9M from tenders that have been recently awarded or are currently under evaluation;
Projects being implemented by NGOs and Local Councils: total of €1M expected expenditure.

## Slide 13: Performance Framework – PA 6 Progress on Output Indicator
Output Indicator | Output Milestone for 2018 | Progress achieved to date | Progress expected to be achieved by end 2018
Urban Development: Public or commercial buildings built or renovated in urban areas | 600 | - | 600
Urban Development: Rehabilitated housing in urban areas | 10 | - | 10
Output indicators are expected to be achieved under the different measures being proposed under this PA.

## Slide 14: Performance Framework – PA 6 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed by end 2018
€6.2M | €2M | €4.2M
The Financial indicator milestone is expected to be achieved under different measures being proposed under this PA.

## Slide 15: Performance Framework – PA 7 Progress on Output Indicator
Output Indicator | Output Milestone for 2018 | Progress achieved to date
KIS: Number of modal shift projects being implemented (constructed) or completed | 1 | 1
The Output milestone has been achieved through the SMITHS project: Introduction of Sustainable Multi Intermodal Transport Hubs across Malta and Gozo project in late 2017.
Notes: OP change: Number of projects and/or schemes being implemented (constructed) or completed
Performance Framework Indicator: Modal shift projects promoting collective transport methods – Target 2023 - 2

## Slide 16: Performance Framework – PA 7 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed by end of 2018
€9M | - | €9M
The selected project under PA 7 has faced huge contracting issues so far, including the fact that 4 tenders with an estimated value of €3.8M have failed in 2018.
No payments have been processed to date, but
€0.5M can be processed shortly from the contracted tenders
€3M are expected from tenders which have been recently awarded but for which contracts need to be signed
€1.3M from tenders under evaluation, and
€4.7M from tenders which are still on the market.

## Slide 17: Performance Framework – PA 8 Progress on Output Indicators
Output Indicators | Output Milestone for 2018 | Progress achieved to date | Progress expected to be achieved by end 2018
Urban Development: Rehabilitated housing in urban areas | 20 | - | 20
Population covered by improved social services* | 10,000* | - | -
The Output Milestone Indicator related to rehabilitated housing should be achieved through the progress being registered under the Regeneration of Social Housing Areas.
The Output Milestone Indicator related to population covered by improved social services is subject to a proposed OP modification to read ‘Population covered by improved health services’: 0
A new proposed Key Implementation Step ‘% of total project public eligible cost contracted: 60%' is also being proposed.
Notes: OP change:
1) Population covered by improved HEALTH services
2) NEW KIS (Nov) - % of total project public eligible cost contracted – 2018: 60%

## Slide 18: Performance Framework – PA 8 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed by end 2018
€14.7M | €2.1M | €12.6M
The remaining forecasted disbursement amounting to €12.6M is expected through the following projects:
Paola Hub Project: €8.1M from tenders that have recently been awarded;
Reach: €4M from main works tender awarded
Regeneration of Social Housing Areas: €1M from various contracts currently being implemented and contracts recently awarded.

## Slide 19: Performance Framework – PA 9 Progress on Output Indicators
Output Indicator | Output Milestone for 2018 | Progress achieved to date | Progress expected to be achieved till end 2018
Capacity of VET and Tertiary education infrastructure | 2,000 | - | 2,000
The Output indicator milestone is expected to be achieved through MCAST Campus project.
Notes: This indicator is pending discussions with MCAST in order to open the building for students in December 2018.

## Slide 20: Performance Framework – PA 9 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed till end 2018
€8.6M | €7M | €1.6M
The remaining forecasted disbursement amounting to €1.6M is expected to be achieved through the following projects:
MCAST Campus Master-Plan: Phase 2 – ca €1.5M will be paid following recent award of contracts and further payments of ca €2.9M are expected if another tender is awarded and no appeals are lodged.
INVEST project – ca €1M will be disbursed through awarded contracts

## Slide 21: Performance Framework – PA 10 Progress on Output Indicator
Output Indicators | Output Milestone for 2018 | Progress achieved to date | Progress expected to be achieved by end 2018
M3 of new/upgraded rainwater retention or storage capacity* | 20,000* | - | -
KIS: No. of waste project being implemented (constructed) or completed** | 1** | - | -
The above indicators are subject to a proposed OP modification as follows:
* Proposed OP modification to remove ‘M3 of new/upgraded rainwater retention or storage capacity: 20,000 sq.m.’ to be substituted by ‘Additional population served by improved water supply: 0’
** Proposed OP modification to remove ‘No. of waste project being implemented (constructed) or completed: 1’ to be substituted by ‘New proposed Key Implementation step ‘% of total project public eligible cost contracted: 60%’.
Notes: OP Change:
M3 of new/upgraded rainwater retention or storage capacity – REMOVED
KIS: No of. WATER project being implemented (constructed) or completed
NEW KIS (Nov) - % of total project public eligible cost contracted – 2018: 60%

## Slide 22: Performance Framework – PA 10 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed till end 2018
€45M | €21.7M | €23.3M
The remaining forecasted disbursement amounting to €23.3M is expected to be materialise under the Water Major project, as well as the three recently approved Waste projects.
All tenders contributing to the disbursement have now been contracted.

## Slide 23: Performance Framework – PA 11 Progress on Output Indicator
Output Indicators | Output Milestone for 2018 | Progress achieved to date
Total length of reconstructed or upgraded roads, of which: TEN-T | 0.5 | 1.5
The Output milestone has been achieved following the conclusion of works on the Kappara Junction.

## Slide 24: Performance Framework – PA 11 Progress on Financial Indicator
Financial Milestone for 2018 | Progress achieved to date | Payments still needed till end 2018
€24.2M | €22.1M | €2.1M
The remaining forecasted disbursement, amounting to €2.1M, is expected to be achieved from contracts awarded under the project focusing on the TEN-T Road Network.