Second Swiss Contribution

Malta

Annual Cooperation Programme Report

| Reporting Period | 18 November 2022 – 31 December 2023 |
| --- | --- |
| Report Number | 1 |
| Report Submission Date | 28.03.2024 |

Table of contents

1.	Executive Summary	4

2.	Cooperation Programme progress	4

2.1	Achievement of objectives of the Cooperation Programme	4

2.2	Status of implementation	4

2.3	Work plan and financial planning	5

3.	Cooperation Programme Management	5

3.1	Management and control systems	5

3.2	Audits	5

3.3	Irregularities	5

3.4	Monitoring and evaluation	5

4.	Communication activities	5

5.	Risk management at the level of the Cooperation Programme	5

Annex 1: Reporting according to Swiss core indicators at Cooperation Programme level	6

Annex 2: Status of implementation	8

Annex 3: Financial status	9

Annex 4: Work plan for the coming year (2024)	10

Annex 5: Financial planning (ongoing Support Measures)	11

Annex 6: Irregularities	12

Annex 7: Monitoring and evaluation plan for the coming years	13

Annex 8: Overview of communication measures at country level during the reporting period	14

Annex 9: Overview of risk assessment on Support Measure Level	15

List of abbreviations

CH	Switzerland

CHF	Swiss Franc

NCU	National Coordination Unit

EA	Executing Agency

FPD	Funds and Programmes Division within the Ministry for European Funds, Equality, Reforms and Social Dialogue

SID	Strategy and Implementation Division within the Ministry for European Funds, Equality, Reforms and Social Dialogue

SDC	Swiss Agency for Development and Cooperation

SM	Support Measure

- Executive Summary

This Annual Cooperation Programme Report has been produced by the Maltese NCU in terms of Article 3.11 of the Regulations on the implementation of the Second Swiss Contribution to selected Member States of the European Union to reduce economic and social disparities within the European Union.

The report covers the period 18 November 2022, being the date when the Framework Agreement between Malta and Switzerland was signed, and 31 December 2023.  It shall be discussed and approved at the Annual Meeting scheduled to held in Malta on 23 April 2024.

The ensuing sections of the report deal with the progress of the Cooperation Programme, physical and financial planning, management, audits, irregularities, evaluations, and communication activities.

Given that the Swiss-Maltese Cooperation Programme consists of a singular SM which had yet to be approved by Switzerland at the cut-off point of this report, the NCU has been able to relate only a limited amount of progress.  It is expected that implementation of the SM will start at pace in April 2024, after signature of the SM Agreement between SDC and the NCU and the conclusion of a corresponding SM Implementation Agreement between the NCU and the Executing Agency.

- Cooperation Programme progress

  - Achievement of objectives of the Cooperation Programme

This is the first Annual Cooperation Programme Report on the implementation of the Second Swiss Contribution to Malta, covering the period 18 November 2022 to 31 December 2023.  The Contribution to Malta forms part of the Second Swiss Contribution to selected Member States of the European Union to reduce economic and social disparities within the European Union.

The Framework Agreement between Malta and Switzerland, including the Country-specific set-up, was signed on 18 November 2022.  At the point of signature of the Framework Agreement, a considerable amount of effort had already been undertaken by SID and SDC on the design and content of the Swiss-Maltese Cooperation Programme; however, with effect from December 2022, FPD, acting as the NCU, took over the work to finalise the Programme in collaboration with SDC.

That process took a further twelve months to complete, until December 2023.  In line with the Framework Agreement, the Swiss-Maltese Cooperation Programme consists of one SM under Specific Objective 4 ‘Strengthening of social systems’, Thematic Area (xi) ‘Health and social protection’.  The whole indicative allocation of the Swiss Contribution amounting to CHF 3.56 million has been earmarked for that SM.  The CHF 3.56 million from Switzerland represents 85% of the project budget with the Malta Government financing the remaining 15%.  In addition to that, Malta will also fund all operational costs following completion of the project as well as the ex-post evaluation.

# The complete, clean version of the SM Proposal was finalised by the NCU towards the end of 2023 for submission to SDC in January 2024.  Formal approval from Switzerland was expected on 25 January 2024, with signature of the SM Agreement foreseen for 23 April 2024 at the first Annual Meeting.  That would mark the official start date (and therefore the first date of eligibility) of the SM Agreement.

  - Status of implementation

As stated, most of 2023 was devoted to defining two Swiss SM Partners in the field of pre-hospital care and cardiology respectively and to finalising the SM Proposal.

Swiss SM Partners

In terms of these Swiss SM Partners, the objective is for them and Ministry for Health and Active Ageing (the Executing Agency) to work closely together and collaborate on the implementation of the training component of the project.

During the reporting period, Swiss Air Rescue REGA and Cardiocentro Ticino were identified as the two Swiss expert institutions.  Following initial contact facilitated by SDC, discussions between them and the Executing Agency have been ongoing with a view to reaching agreements on the provision of training and consultancy to Accident and Emergency Personnel on pre-hospital care as well as training to two Cardiology Fellows in specialised fields of cardiology to further improve the care of Maltese cardiac patients.  As of 31 December 2023, these discussions were still in progress but all parties were optimistic of their successful conclusion.

SM Proposal

Aside from preparatory work like tender document drafting, no project implementation incurring eligible expenditure could take place during the reporting period, it being wholly prior to the first date of eligibility.

On 22 December 2023, the NCU and SDC agreed that the final, clean version of the SM Proposal would be formally submitted for Switzerland’s approval by 15 January 2024.  After approval by Switzerland (towards the end of January 2024), an SM Agreement would need to be concluded between the NCU and SDC.  This would then be followed by an SM Implementation Agreement between the NCU and the Executing Agency, enabling implementation could start.

Framework Agreement

# There have been no amendments to the Framework Agreement and its Annexes during the reporting period.

  - Work plan and financial planning

Key activities in 2024:

April 2024 – Signing of Partnership Agreements with Cardiocentro Ticino and Swiss Air Rescue REGA

April 2024 – Signing of the SM Agreement

April 2024 – First Annual Meeting

April 2024 – Signing of the SM Implementation Agreement

April 2024 – Launch of Project Management Services tender

May 2024 – Launch of calls for the selection of cardiologists and A &E personnel

September 2024 – Launch of tenders for the supply, installation and commissioning of a single plane cardiac Cath Suite and a Coronary Robotic control system

September 2024 – Signing of Project Management Services contract

October 2024 – First Meeting of the SM Steering Committee

# December 2024 – First Reimbursement Request to Switzerland

- Cooperation Programme Management

  - Management and control systems

# No changes to the setup and staffing of the national authorities involved in the management and control system took place during the reporting period.

  - Audits

In accordance with Article 9.3 of the Regulation, the Audit Authority prepared the Audit Strategy for the Cooperation Programme.  This was submitted to SDC on 14 August 2023.  On 4 September 2023, SDC approved it subject to conditions.  To address those conditions, the Audit Authority submitted a revised Strategy on 12 October 2023.  On 26 October 2023 SDC informed the Audit Authority that after having reviewed the documentation it could confirm that the conditions had been fully met.

# As implementation of the SM had not yet started, no audits were performed by the Audit Authority during the reporting period.

  - Irregularities

# No complaints were received through the complaint mechanism athttps://fondi.eu/contact-us/.  Furthermore, no irregularities were reported or detected during the reporting period.

  - Monitoring and evaluation

The monitoring and evaluation plan in terms of Article 10.1 of the Regulation is at Annex 7 of this report.  In view of the lack of a technical assistance budget under the Programme, the NCU proposes to use national funds to finance the ex-post evaluation foreseen for 2027-2028.

# Given that the SM was still to be approved at the cut-off date of this Annual Report, no monitoring or evaluation activities took place during the reporting period.

- Communication activities

Since implementation of the SM was not yet underway, no communication activities related specifically to it took place during the reporting period.

It is worth noting here that the decision was taken early on – presumably during the Framework Agreement negotiation phase, and so before FPD became involved as the NCU for the Programme – that 100% of the Swiss Contribution would be allocated to one SM under Specific Objective 4 ‘Strengthening of social systems’, Thematic Area (xi) ‘Health and social protection’ and to do away with technical assistance.  That, in turn, has meant that there is no provision for communication activities at the level of the Cooperation Programme, since these are normally funded through the technical assistance budget.

The NCU has been given to understand that the reason for that decision was that the Programme consists of just the one SM, thus making the SM coterminous with the Programme.  The SM budget does include an allocation for publicity and communication activities.  Although the Executing Agency is responsible for the implementation of communication activities at the SM level, these shall be designed in consultation with the NCU to take account of the Programme level perspective.

Meanwhile, the Ministry of Foreign Affairs has published the Framework Agreement signed on 18 November 2022 on its website.  The event was also reported in the national press and media:

https://foreign.gov.mt/wp-content/uploads/Treaties/Framework%20Agreement%20between%20the%20Swiss%20Federal%20Council%20and%20the%20Government%20of%20the%20Republic%20of%20Malta.pdf

# Information about the Second Swiss Contribution and the Swiss-Maltese Cooperation Programme can also be found on the Government of Malta’s EU and EU-accession related funding website: https://fondi.eu/programme/swiss-maltese-second-contribution-programme/

# https://fondi.eu/programme/swiss-maltese-second-contribution-programme/

- Risk management at the level of the Cooperation Programme

# The overall level of risk of the SM (and therefore of the Cooperation Programme) is assessed as Low to Medium.  The assessment, including the NCU’s comments, are at Annex 9.  At this pre-implementation stage no risks which jeopardise the implementation of the SM or the entire Cooperation Programme have been identified.

# Annex 1: Reporting according to Swiss core indicators at Cooperation Programme level

| Core Indicator, incl. definition and units | Baseline | Target | Achieved this period | Cumulatively achieved | Cumulatively achieved as percentage of target |  |
| --- | --- | --- | --- | --- | --- | --- |
| HEA_CI_1 Number of people reached with improved healthcare measures |  |  |  |  |  |  |
| Outcomes |  |  |  |  |  |  |
| Increased number of Structural Heart procedures | 65 procedures | 90 procedures in Year 1 after completion of the third Cardiac Cath Suite, going up to 115 in Year 2 and 145 in Year 3 | - | - | - |  |
| Reduced waiting times for Structural Heart procedures | 180 days | 90 days | - | - | N/A |  |
| Increased number of Ablation procedures. | 86 procedures | 120 procedures in Year 1 after completion of the third Cardiac Cath Suite, going up to 145 in Year 2 and 180 in Year 3 | - | - | - |  |
| Reduced waiting times for ablation | 110 days | 60 days | - | - | N/A |  |
| Corononary Robotic procedures introduced | 0 | 80 procedures per year after completion of the third Cardiac Cath Suite | - | - | - |  |
| Outputs |  |  |  |  |  |  |
| Single Plane Cardiac Cath Suite installed | 0 | 1 | - | - | - |  |
| Coronary Robotic Control System for the Cardiac Cath Suite installed | 0 | 1 | - | - | - |  |
| Cardiac health Awareness Campaign implemented | 0 | 1 | - | - | - |  |
| Cardiac Fellows trained | 0 | 2 | - | - |  | - |
| Accident and Emergency Personnel trained in pre-hospital care | 0 | 10 | - | - |  | - |

# Annex 2: Status of implementation

| SM name including Swiss and Partner State SM codes | Status | Swiss contribution to the SM in CHF | Start date | End date | SM Agreement and Amendments (dates of entry into force) | Reporting status | Assessment of progress by NCU |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Comprehensive Response to Heart Diseases MESC/FPD/03/2024 | 2nd stage proposal approved by Switzerland | CHF3,560,000 | 23.04.2024 | 31.12.2028 | 23.04.2024 | on track | on track |

# Annex 3: Financial status

| SM name including Swiss and Partner State SM codes | Swiss contribution to the SM [CHF] | Total reimbursements received from CH [CHF] |  | % of Swiss contribution to the SM received from CH |
| --- | --- | --- | --- | --- |
| Comprehensive Response to Heart Diseases MESC/FPD/03/2024 | CHF 3,560,000 | CHF 0 |  | 0% |
| Total | CHF 3,560,000 |  | CHF 0 | 0% |

# Annex 4: Work plan for the coming year (2024)

| SM name including Swiss and Partner State SM codes | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comprehensive Response to Heart Diseases MESC/FPD/03/2024 | 2nd SMP |  |  | SMA |  | P |  |  | P | SC |  | P |
| Cooperation Programme level | 2nd SMP |  |  | SMA |  | P |  |  | P | SC |  | P |

Key activities in 2024:

April 2024 – Signing of Partnership Agreements with Cardiocentro Ticino and Swiss Air Rescue REGA

April 2024 – Signing of the SM Agreement

April 2024 – First Annual Meeting

April 2024 – Signing of the SM Implementation Agreement

April 2024 – Launch of Project Management Services tender

May 2024 – Launch of calls for the selection of cardiologists and A &E personnel

September 2024 – Launch of tenders for the supply, installation and commissioning of a single plane cardiac Cath Suite and a Coronary Robotic control system

September 2024 – Signing of Project Management Services contract

October 2024 – First Meeting of the SM Steering Committee

December 2024 – First Reimbursement Request to Switzerland

Abbreviations:

First stage SM Proposal submitted to CH: 1st SMP

Second stage SM Proposals submitted to CH: 2nd SMP

Signature of SM Agreement: SMA

Call for proposals: CP

Communication activity: C

Submission of tender documents to CH for assessment: P

Monitoring Mission: MM

Evaluation: EV

Audit: AU

Steering Committee Meeting: SC

Submission of SM Completion Report to CH: SMC

# Annex 5: Financial planning (ongoing Support Measures)

| SM name including Swiss and Partner State SM codes | Swiss contribution to the SM[CHF] | Reimbursements planned to be requested from CH [CHF] |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 2024 | 2025 | 2026 | 2027 | 2028 |
| Comprehensive Response to Heart Diseases MESC/FPD/03/2024 | CHF3,560,000.00 | CHF11,138.18 | CHF147,572.40 | CHF1,392,078.24 | CHF1,998,072.99 | CHF11,138.19 |

# Annex 6: Irregularities

| SM name including Swiss and Partner State SM codes | Irregularity reference number | Swiss contribution to the SM in CHF | Nature of actual or suspected irregularity | Estimation of total financial damage in CHF (if any) | Proposed financial correction in case of financial damage | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Comprehensive Response to Heart Diseases MESC/FPD/03/2024 | Not applicable | CHF 3,560,000 | Choose an element. | Not applicable | Not applicable |  |
|  |  |  | Choose an element. |  |  |  |
|  |  |  | Choose an element. |  |  |  |
|  |  |  | Choose an element. |  |  |  |

There are no irregularities to report.  The Support Measure was not yet under implementation during the period covered by this Annual Cooperation Programme Report.

# Annex 7: Monitoring and evaluation plan for the coming years

A.	Overview

| SM name including Swiss and Partner State SM codes | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Comprehensive Response to Heart Diseases MESC/FPD/03/2024 |  |  |  |  |  | M |  |  |  | M |  |  |  | M |  |  |  |  |  |  |
| Cooperation Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  | E | E | E | E |  |  |

Monitoring visit: M

Evaluation: E

B.	Additional information on the strategic planning of evaluations

The Swiss-Maltese Cooperation Programme consists of a single Support Measure.  This means that the Support Measure and the Cooperation Programme are coterminous.  In view of this, it is envisaged that the NCU will launch a departmental tender for an ex-post external evaluation at the Programme level following completion of the Support Measure, currently projected during H1 2027.  The plan is to publish the call for tenders during Q2 2027, with the contract being awarded in Q3 2027.

The proposed external ex-post evaluation would be expert-driven and intended to assess the Swiss-Maltese Cooperation Programme and the Support Measure from the relevance, efficiency, effectiveness sustainability and (likely) impact perspectives.  The evaluation should also identify key lessons and recommendations.

Since the Cooperation Programme does not include a technical assistance budget, national funds would need to be allocated for this exercise.

# Annex 8: Overview of communication measures at country level during the reporting period

| Communication measure | Positive results in terms of visibility and awareness of the Cooperation Programme and CH’s image (media response, feedbacks etc.) | Lessons learnt (e.g. related to (timing, place, adjustment to target groups, use of logo etc.) |
| --- | --- | --- |
| Framework Agreement Signing ceremony | Reported in the national press and media |  |

No SM or Programme specific communication measures were implemented during the reporting period covered by this Annual Cooperation Programme Report.  That is because the Support Measure Proposal was not yet approved by Switzerland and so implementation was unable to commence.

Since (a) the Support Measure and the Cooperation Programme are coterminous, (b) there is no technical assistance budget at the Programme level and (c) the Support Measure already includes a budget of €16,157.76 [CHF15,398.35] for this use, the Project Operator of the Support Measure will lead the implementation of the communication measures.  The NCU should be closely involved in the preparation and design of the measures.  On current projections communication measures are foreseen during 2025 and 2027.

It is worth noting however, that the Ministry of Foreign Affairs has published the Framework Agreement signed on 18 November 2022 on its website.  The signing event was reported in the national press and media.

# Annex 9: Overview of risk assessment on Support Measure Level

| SM name including Swiss and Partner State SM codes MESC/FPD/03/2024 | Overall risk | Assessment and comments by the NCU |
| --- | --- | --- |
| Comprehensive Response to Heart Diseases | Low-Medium | The Support Measure identifies seven (7) risks, two (2) of which are rated as ‘Medium’. These are: Environmental risk – This is the risk associated with the end-of-life disposal of the equipment being procured through the project. As Project Operator of the SM, the Ministry for Health and Active Ageing must take care to dispose of the equipment in line with relevant regulations in force at the time, including recycling where possible. Public procurement risks – Public procurement has been highlighted as a risk to this project being completed on time. Public procurement risks present themselves at every stage of the process, from tender launch all the way through to delivery, installation and commissioning of the equipment. The risks include delays in the publication of the the tender document, non-receipt of compliant offers, the tender evaluation taking more time than initially anticipated, the possibility of an objection to the recommendation of award being lodged, delays in the manufacturing, shipping and delivery of the equipment and complications arising during the installation and commissioning phase. In planning the project, the Project Operator has designed the implementation schedule in a way to take account of these risks. |

# The first Support Measure Annual Report is due in 2025.  Accordingly, NCU should be in a position to perform the risk assessment per the above instructions in the Annual Cooperation Programme Report for the period ending 31 December 2024.

# In terms of the present Report, the assessment has been based on the risks identified in the final Support Measure Proposal as submitted to Switzerland on 15 January 2024.